## Sheet1
Sr. No. | Functionality List | Status
1 | Weapons needs to added | Done
2 | Enemy needs to be added | Done
3 | Rock obstacle collider | Done
4 | More Enemy needs to be added | Done
5 | Navigation | Done
6 | Canavas UI Design | Done
7 | Help Instruction | Pending
8 | Game timer for different Levels | Done
9 | Level 1 Testing | Done
10 | Level 2 Testing | Done
11 | Level 3 Testing | Done

## Level 1 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Priority | Status | Status 25 April 2018
TC_1 | Level 1 > After pressing space button | It should attack or move forward | Character stops at one point and doesn’t move further once pressed spacebar key | High | Closed | Done
TC_2 | Level 1> Character movement | Character movement should be little faster | Character is moving with low speed | Medium | Closed | Done
TC_3 | Level 1> Minimap | Minimap should show in Level 1 | Minimap is not showing under Level 1 | Medium | Closed | Done
TC_4 | Level 1 > Enemy collider | Enemy collider should work with character | Enemey collider is not working | High | Closed | Done
TC_5 | Level 1> Weapon | Weapons needs to be added | Weapons needs to be added | High | Closed | Done
TC_6 | Level 1 > Timer | After Timer finishes player should lose the game | Timer is going in negative cycle. | Medium | Closed | Done
TC_7 | Level 1 > Finish line | After Level 1 finishes, Level 1 Finish message should pop-up | No message | Low
TC_8 | Level 1> Score Mechanism is not working | Score should be added after player kills enemy | It is not updating the score | High |  | Open

## Level 2 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Priority | Status | Status 25 April 2018
TC_1 | Level 2> Weapon | Weapons needs to be added | Weapons needs to be added | High | Done | Done
TC_2 | Level 2 > Enemy collider | Enemy collider should work with character | Enemey collider is not working | High | Closed | Done
TC_3 | Level 2 > Timer | After Timer finishes player should lose the game | Timer is going in negative cycle. | High | Closed | Done
TC_4 | Level 2 > Spikes | Spikes should reduce HP | HP reduction functionality needs to be implemented | High | Closed | Done
TC_5 | Level 2 > Finish line | After Level 2 finishes, Level 2 Finish message should pop-up | No message | Low
TC_6 | Level 2 > After pressing space button | It should attack or move forward | Character stops at one point and doesn’t move further once pressed spacebar key | High | Closed | Done
TC_7 | Level 2> Character movement | Character movement should be little faster | Character is moving with low speed | Medium | Closed | Done
TC_8 | Level 1> Score Mechanism is not working | Score should be added after player kills enemy | It is not updating the score | High |  | Open
TC_10 | Level 1> Minimap | Minimap should show in Level 1 | Minimap is not showing under Level 1 | Medium | Closed | Done

## Level 3 Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Priority | Status | Notes
TC_1 | Level 3 > Weapon | Weapons needs to be added | Weapons needs to be added | High | Done
TC_2 | Level 3 > Enemy collider | Enemy collider should work with character | Enemey collider is not working | High | Closed | Done
TC_3 | Level 3 > Timer | After Timer finishes player should lose the game | Timer is going in negative cycle. | High | Closed | Game instruction are disppearing after game over
TC_7 | Level 3 > Finish line | After Level 1 finishes, Level 1 Finish message should pop-up | No message | Low
TC_8 | Level 3 > Difficulty level | More difficulties needed | Less Enemy | Medium
TC_9 | Level 1 > After pressing space button | It should attack or move forward | Character stops at one point and doesn’t move further once pressed spacebar key | High | Closed | Done

## Wallace Feedback_Beta_Release
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Priority | Status
ISSUE_1 | Level 1 > After pressing space button. Attack causes the character to spin and also prevent the player from moving at all. Given the amount of enemies in each level this is a game-breaking bug that needs to be addressed immediately. | It should attack or move forward > Character stops at one point and doesn’t move further once pressed spacebar key |  | High | Done
ISSUE_2 | Some enemies (bugs) seem to move freely between a solid platform and liquid. This should be corrected to make the enemies more believable | Collider for the Enemies |  | High | Done
ISSUE_3 | Also the enemies all do the exact same thing (move between 2 points). You should implement more variety such as have enemies chase the player or only move when the player is visible.Repetitive movements across multiple enemy types is lazy | AI for enemies |  | High | Open
ISSUE_4 | Version history is missing descriptions of each version of the document and the changes made. | Documents needs changes |  | High | Done
ISSUE_5 | Elaborate on mechanics. "Kill enemies by attacking". Attack with what? A laser? A punch? Be specific. | Specific attack instructions need to be added after adding attack mechanism |  | High
ISSUE_6 | Maps should have descriptions for each describing how they are each different from one another. | Map descripts needs to be added under about game |  | High
ISSUE_7 | Visual: Document looks bland and uninspiring with only italics placed on the text. Needs more images and a unique font to make the document stand out. | Documents needs more images and unique fonts |  | High | Done
Overall Feedback | Improvement: Looking for more improvement. Your game had a significant jump in quality from previous submissions but your document didn't receive that jump in quality. |  |  |  | Done

## Final_WB_GL_Testing
Test Case_ID | Test Case Descrpition | Expected Result | Actual Result | Priority | Status
TC_1 | Movement between 3 different Levels are working | Characters should move between all three levels | Characters should move between all three levels | High | Done
TC_2 | All the mechnism should work fine at all three levels | All mechanism should work fine at all three levels | All the mechanism are working fine for all three levels | High | Done